Error: Reference source not found

Table of Contents

1	Scope of Application	3

2	Purpose	3

3	Definitions	3

4	Applicable Documents	4

5	Responsibility and Workflow	4

5.1	Recording of damage or loss	4

5.2	Recording of deliveries not conforming to specifications	5

5.3	Assessment and initiation of corrective measures	6

5.4	Decision on further actions	6

5.5	Closure of corrective actions	6

6	Performance	8

7	Documentation, Quality Records	8

8	Amendments	8

9	Distribution	8

10	&AA-W-DW 0803 Overage, Shortage and Damage Report (OS&D)	10

11	&AA-W-DW 0813 (EN) Concession Request for Components	11

# Scope of Application

This work instruction applies to the damages, losses and deliveries not conforming to specifications of equipment and materials to the construction site warehouse identified during receipt, inspection, storage or assembly.

# Purpose

This work instruction ensures that damaged parts are excluded from being used and that actions for compensation or replacement in case of loss are initiated.

For this purpose, this work procedure describes how to record, document, initiate and take corrective actions as well as any special measures for safeguarding possible insurance claims and the rights of recourse.

# Definitions

| CLIENT | The company who awarded the contract to Linde LE. |
| --- | --- |
| COMPANY | Linde AG, Gas and Engineering, Linde Engineering Division, Munich, hereinafter referred to as “COMPANY”, who manages and monitors all construction and erection activities that are within its scope of the contract and usually procures all the required equipment, materials and services. |
| CONTRACTOR | The company being engaged by COMPANY for the execution of all material management and warehousing activities according to the purchase order and the related scope of work for these services. |
| OS&D | Report for Overages, Shortages, Non-Conformities and Damages, as well for the definition of corrective measures |
| Non-Conformity | Non-performance of a defined requirement associated with an order transaction, including corresponding documentation (e. g. technical delivery conditions) |
| Equipment | This term refers to all items such as apparatus, machinery, package units - procured and delivered by COMPANY or Third Party. |
| CRC | Concession request for Components Application and approval form sheet for concession request of a non-conformity of a specified (ordered) item |
| PCM | Project Construction Manager |
| SSI | Site Superintendent |
| Materials | This term refers to sheet metal, piping materials, semi-finished products, electrical materials, instrumentation materials, cables and spare parts, etc. - procured and delivered by COMPANY. |
| Damage | This term refers to visible or concealed damage to equipment and materials caused by improper handling, operating error or by other external influences (e.g. force majeure), that make the item completely or partly unusable. |
| Loss | This term refers to parts that are lost during transport, storage or assembly. |
| Insured party | A company (e. g. COMPANY or CONTRACTOR) who has covered its risks in supplies and services against damage or loss or other external influences |
| Insurer | An organization that provides insurance coverage to the insured party for contractually agreed risks. |

# Applicable Documents

| &AA-W-DW 0803 | Overage, Shortage and Damage Report (OS&D) |
| --- | --- |
| &AA-W-SC 0801 (EN) | Material receiving, Inspection, Release and Site Procurement for Equipment and Materials |

# Responsibility and Workflow

## Recording of damage or loss

Each employee on site who identifies any damage or loss is immediately obliged to:

  - Record the damage or loss in an OS&D (see section 10). At least, the location and time must be noted and if identifiable, the name of the accountable party and if applicable, the names of witnesses. The course of events and the cause(s) for the damage or loss have to be described briefly but clearly.

  - Forward the OS&D to COMPANY.

In case of damages and deliveries of items not conforming with specification respectively, any further use of the damaged part shall be prevented by marking it as "quarantine" and as far as possible storing it in a way that it cannot be issued, passed on, used, processed or altered prior to completion of corrective actions.

Each OS&D shall be numbered administrated by Material Administration and handed over to the Lead Material Administration of COMPANY for further processing.

The Lead Material Administration of COMPANY is responsible for the prompt processing, the closing and documentation of the OS&D.

The damage or loss recorded in the OS&D is to be confirmed by the signatures of the accountable party (if known) and / or COMAPNY.

Damages and losses for the purpose of this specification are:

For the purpose of this work instruction, an OS&D shall be issued, but not limited to, in case of:

  - Transport damage

This refers to any damage or loss that occurs during transport from the shipping location to the construction site as a result of improper packaging or inadequate securing of the goods etc.

  - Assembly damage

This refers to any damage or loss that occurs during storage or assembly. This is any damage or loss caused by improper handling of the goods during unloading in the warehouse, during intermediate transport on the construction site, storage-related damage or loss (e. g. corrosion, theft), as well as damage or loss during installation of the equipment and materials etc.

The preparation of an OS&D is independent of the person or circumstances that caused the damage or loss, or the likely extent of the damage.

With the identification of a damage / loss, the COMPANY'S Administrator Site Contracts shall check whether the costs and / or course receivables could be covered by the insurance and / or the accountable party.

### Insurance benefits

Hence, COMPANY prescribes the following basic rules to be complied with for damage involving transport or assembly.

  - The insurer has to be informed about the damage immediately, but in any case within the notification deadline.

  - A request for damage assessment has to follow the notification and if applicable, a relevant appointment has to be made.

  - Damaged goods have to be kept in their discovered state until the insurer has either assessed the damage or dropped in writing his rights for inspection.

  - In case of major damage it is advisable to take photos.

  - If applicable, particular attention shall be paid to possible special reporting forms as well as the right of the insurer to clear the damage.

#### Additional aspects to be considered regarding transport damage

Immediately upon arrival of the goods at the unloading location specified by COMPANY and if possible, prior to unloading, the number of packages and the goods should be checked. At least the packaging should be checked for externally visible damage.

Any identified or even suspected damage or loss has to be noted on the shipper’s freight documents. In case of concealed damage not externally recognizable, i.e. damage that can be identified only after removal of the packaging, the goods have to be left in the state in which they were found. Any further handling of the damage is permissible only after discussion and agreement with the insurer.

#### Special situations

An action deviating from or not complying with the conditions and guidelines to safeguard insurance benefits is permissible in cases where safety consequences, i.e. either the endangerment of persons and the environment or the obligation to limit damages, require that other immediate actions are taken. These actions shall always be in agreement with the PCM and the Construction Site Manager or optionally with the Site QA/QC and Site HSE Manager.

### Rights of recourse

For safeguarding the rights of recourse, the name of the accountable party, the location, time and names of witnesses have to be recorded in the OS&D. To secure evidence, photos (digital camera) are to be taken. The chain of events leading to the damage and its extent has to be confirmed by the signature of the party accountable, when known.

## Recording of deliveries not conforming to specifications

Each employee on site who identifies any deliveries not conforming to specification is immediately obliged to:

  - Prevent any further use of the corresponding part by marking it as "quarantine" and, if possible, storing it in a way that it cannot be passed on, processed or altered prior to completion of corrective actions.

  - Record the deliveries not conforming to specifications in an OS&D (see section 10). The identified non-conformity of the specified requirement shall be explicit, e. g. deviation of wall thickness Target: 12 mm, Actual 10 mm.

  - Forward the OS&D to COMPANY.

Each OS&D shall be numbered and administrated by Material Administration and handed over to the Lead Material Administration of COMPANY for further processing.

The Lead Material Administration of COMPANY is responsible for the prompt processing, the closing and documentation of the OS&D.

In the context of this specification deliveries not conforming to specification are:

  - Missing or wrong marking (basically Ident No., material, heat number)

  - Wrong material (e. g. Stainless Steel instead of Carbon Steel), if not a substitute is especially approved by a concession request (refer to &AA-W-SC 0801 (EN) "Material Receiving, Inspection)

  - Wrong item, e. g. 45° elbow instead of 90° elbow

  - Visual defects on the part itself as well as welding, cleanliness, coatings, preservation, etc.

  - Functional defects, e. g. rusting of stems, wrong display of temperature or pressure

  - Other defects / deficiencies and / or non-compliance to requirements according to order, technical specification, etc.

## Assessment and initiation of corrective measures

The responsible person of COMPANY (e. g. mechanics, electrical engineering) shall conduct a detailed inspection and assessment of the extent of the damage or loss and recommend the corrective actions to be initiated.

The following corrective actions are possible:

  - Acceptance, toleration and special release (with justification, and if necessary, under specific conditions). This is applicable only in cases of minor damage like a scratched surface coating etc.

  - Repairs (detailed repair procedure required) and clarification of reimbursement prior to start of repair

  - Rejection (discarding) of damaged parts / deliveries not conforming to specifications together with actions for a new delivery or credit voucher instead of delivery

  - Replacement of lost parts

## Decision on further actions

Construction Manager and Construction Site Manager of COMPANY have to decide the realization of recommended actions while observing the following rules:

All decisions on the redress of any damage, loss or deliveries not conforming to specification have to be confirmed in the OS&D by signature of COMPANY'S Site QA/QC Manager.

Actions which will have an impact the contractual relationship between COMPANY and CLIENT have to be approved by the Project Management of COMPANY and CLIENT respectively.

Actions which will have an impact compliance with official regulations have to be cleared by COMPANY with the relevant authority.

Actions which will have an impact the contractual relationship with the supplier of the goods have to be cleared and confirmed with this supplier by COMPANY'S Administrator Site Contracts.

In case of damage, loss and deliveries not conforming to specifications for which the supplier is responsible, the right to make repairs is generally with the supplier, because of the need to safeguard any warranty claims. Exceptions to this rule shall, in regards to deadlines, be approved by COMPANY'S Site Manager.

## Closure of corrective actions

### Organizational process

The SSI Material Management of COMPANY shall arrange, coordinate and trace with the accomplishment of all the economic and technical actions. The evaluation of the correct procedure for redressing the damage shall be carried out by the Site QA/QC Manager.

The department Procurement (B) of COMPANY shall conduct the actuarial aspects.

Any actions taken have to be fully documented in original in the OS&D and confirmed with signature after correct closure by the SSI Material Management of COMPANY.

### Corrective measures

#### Acceptance, tolerance, special release

The SSI Material Management of COMPANY shall justify the action to be taken in written and in detail. The OS&D is deemed closed when the damaged parts are released for further use.

#### Repairs

Any repairs to be carried out depend on the situation and schedules as well as the supplier’s agreement and shall be done

  - By the supplier on the construction site (delegation of a supplier’s specialist)

  - By the supplier at the manufacturer’s plant (parts returned to the manufacturer)

  - By the construction site assembly personnel or by third parties in a local workshop.

The work has to be carried out as per COMPANY'S instructions. If required, a separate work order shall be issued.

Prior to start of work it shall be defined who is responsible for covering the expenses. After completion and inspection of the work by COMPANY, the technical part of the OS&D is deemed closed and the components shall be released for further use.

All incurred expenses shall be evaluated and recorded for each OS&D. In justified cases the accountable party will be charged.

#### Rejection and replacement

By submitting the OS&D, the supplier is demanded to either

  - Deliver new parts within a reasonable period of time or

  - Agree that COMPANY itself procures new parts on supplier's expense or

  - Issue a credit voucher, if the procurement of new parts is not required anymore.

After completion of the named measures, the OS&D is deemed closed.

On demand of the supplier the rejected parts shall be returned on its expenses.

Rejected equipment and materials shall be precluded from further use, identified with the relevant OS&D–No. and stored in a specially marked quarantine area (shelf).

### Determination of costs

All related costs incurred by damage / loss and delivery not conforming to specification are to be documented so that they are fully traceable and provable. All persons involved are obligated to assist in determining the costs.

This applies in particular to the following:

  - Costs for new components

  - Repair costs

  - Additional transport charges

  - Additional work conducted by Linde’s and Contractor’s personnel.

# Performance

# Documentation, Quality Records

The documentation of all damages / losses and deliveries not conforming to specification identified, including related decisions on further measures and confirmation of the corrective actions carried out is handled in the OS&D. The SSI Material Management of COMPANY shall archive the original report.

# Amendments

Amendments or recommendations shall be informal sent in writing to the Head of Department "Construction Mechanical" GCLM.

# Distribution

The OS&D report shall be distributed to the following group of people:

  - COMPANY (departments: project management, procurement (B), Lead Material Administration)

  - Insurance company and/ or the party accountable

  - Supplier

This procedure is not subject to any confidentiality requirements and is available for employees of The Linde Group or external parties with legitimate interests.

The Reference Process Manager allocates the access rights in Documentum and is responsible for the distribution and publication of this work instruction.

# &AA-W-DW 0803 Overage, Shortage and Damage Report (OS&D)

# &AA-W-DW 0813 (EN) Concession Request for Components